ENS 491-492 – Graduation Project

Final Report

Project Title: Project Management Simulation Game

Group Members:

Ceren Kılınç

Orhun Ozan Koyuncu

Damla Yurtkulu

Öykü Can

Zeynep Gökmen

Aslı Gökmen

Supervisor(s): Gündüz Ulusoy

Date:24/05/2026

1. EXECUTIVE SUMMARY	3

2. PROBLEM STATEMENT	4

2.1. The Main Problem /Motivation	4

2.2. Objectives/Tasks	4

2.3. Realistic Constraints	6

2.3.1. Resource Constraint	6

2.3.2. Time Constraint	7

2.3.3. Budget Constraint	8

2.3.4. Scope Constraint	9

3. METHODOLOGY	10

3.1. Activity Network Diagram	10

3.2. CPM Analysis	13

3.3. Scenario System	15

3.3.1. In Game Scenarios	15

3.3.2. Festival Day Scenarios	17

3.4. Feedback Page	25

3.5. Decision Mechanism and Scoring System	27

3.6. Godot Engine Implementation	29

4. RESULTS & DISCUSSION	33

5. IMPACT	35

6. ETHICAL ISSUES	37

7. PROJECT MANAGEMENT	38

7.1. Initial Project Plan	38

7.2. Changes During Implementation	38

7.3. Final Project Plan /Lessons learned	38

8. CONCLUSION AND FUTURE WORK	39

8.1. Conclusion	39

8.2. Future Work	39

9. APPENDIX	40

10. REFERENCES	45

# EXECUTIVE SUMMARY

This project focuses on designing and implementing a single-player project management simulation game that allows players to experience the challenges of managing a complex project under time, budget, scope, and resource constraints. The main objective of the project is educational rather than competitive; the game is designed to teach project management concepts through active participation and decision-making instead of relying only on theoretical explanations. The simulation is based on organizing a university festival, where the player acts as the project manager responsible for planning and coordinating the entire event lifecycle.

Throughout the game, the player manages several interconnected activities including team selection, sponsor negotiations, promotion strategy, ticket pricing, vendor selection, stage and sound system decisions, transportation coordination, layout planning, security and cleaning management, and risk preparation. Each decision directly affects different project performance indicators such as budget usage, participant satisfaction, event quality, resource efficiency, time management, and scope adherence. The game starts with an initial project budget, and player decisions continuously increase or decrease the remaining budget depending on the quality and cost of selected options. The simulation starts with an initial project budget of 400,000 TL. If the project budget decreases to -300,000 TL or below at any point during the game, the project is considered financially unsustainable and the simulation ends immediately. This financial policy was designed to encourage players to balance cost, quality, and resource allocation decisions carefully throughout the project lifecycle.

The project incorporates several project management techniques and mathematical models. A Critical Path Method (CPM) model was developed to identify task dependencies, calculate activity timings, determine slack values, and identify critical activities. In addition, all players start the simulation with the same initial project duration and baseline conditions to ensure fairness in evaluation. To measure the player’s ability to react to unexpected situations, the game includes dynamic in-game scenarios that represent real-life project risks and crises. These scenarios may create unexpected task delays and additional time durations, forcing the player to reorganize resources, schedules, and priorities under pressure. This structure allows the simulation to evaluate not only planning performance but also adaptability and decision-making during unforeseen project events. The implementation was developed in the Godot Engine using a modular panel-based architecture and a centralized game state management system.

The final evaluation system of the game is based on multiple performance categories that are calculated and presented separately to the player. Categories such as budget control, time management, participant satisfaction, event quality, scope adherence, and resource-related performance are evaluated independently to provide more detailed feedback. The main purpose of this structure is not to rank players through a single overall score, but to help them understand their strengths and weaknesses in different project management dimensions. For example, a player may perform well in budget control but have lower event quality, or may create a highly satisfying festival experience while facing time or budget problems. Therefore, each performance category is shown separately so that players can reflect on their decisions instead of simply competing for one final score. To ensure fairness and comparability between different metrics, non-dimensional evaluation methods were preferred during score calculation. This allows different performance indicators to be normalized and assessed within the same scoring structure regardless of their original scales or units.

The main conclusion of the project is that the simulation successfully connects project management theory with practical decision-making in an interactive environment. Rather than encouraging competition, the game aims to improve players’ understanding of planning, budgeting, resource allocation, scheduling, and risk management throughout a project lifecycle. Overall, the project provides an educational and realistic simulation environment that supports learning project management concepts through experience-based gameplay.

# PROBLEM STATEMENT

## The Main Problem /Motivation

Project management requires coordination of time, budget, scope, resources, risks, and stakeholder expectations at the same time. Although these concepts are usually taught through lectures, formulas, and case studies, students may find it difficult to understand how project management decisions affect each other in a real project environment. For example, reducing cost may lower the output quality, adding resources may improve time performance but increase expenses, and poor risk planning may create problems during implementation.

The main problem addressed in this project is the lack of an interactive learning environment where students can experience these trade-offs directly. In traditional education, methods such as CPM, budgeting, resource allocation, and risk management are often explained separately. However, in real projects, these elements are strongly interconnected and must be managed together.

The motivation of this project is to transform project management learning into a practical and engaging simulation. The game uses the organization of a university festival as the project scenario because it includes realistic activities such as team selection, task assignment, sponsor management, promotion, ticket pricing, vendor selection, layout planning, and emergency management. Through these activities, the player can observe how each decision affects project performance.

Existing project management simulations and educational tools generally focus on specific parts of project management, such as scheduling or cost control. This project aims to combine multiple project management dimensions in one game-based environment. Therefore, the goal is to help students learn by doing and understanding the relationships between planning, resource use, budgeting, scope control, and risk management.

## Objectives/Tasks

The main objective of this project is to develop an educational project management simulation game that enables players to experience planning and executing a university festival project. The objectives, learning outcomes, and implementation methods are listed below:

2.2.1. Apply project planning processes, including task prioritization, timeline creation, and resource allocation.
Learning objective: Players will learn to plan and schedule tasks effectively during the project’s planning phase.

This objective is implemented through the early planning activities of the game. In a team assignment, players select members with different skills and capacities. In a work assignment, they assign these members to project activities by considering workload limits and task requirements. The Gantt chart and activity dependencies help players understand the order of tasks, while transport coordination supports timeline planning by requiring correct delivery timing.

2.2.2. Develop decision-making skills in resource and cost management under constraints.
Learning objective: Players will improve their ability to make trade-offs among cost, resources, and time under realistic constraints.
	This objective is implemented by giving players a limited budget, team capacity, and operational resources. Activities such as emergency training, sponsor management, transport coordination, and resource allocation require players to compare alternatives. For example, training team members improves emergency response but increases cost, while additional resources may support the schedule but reduce the remaining budget.

2.2.3. Analyze and respond to risks and unexpected situations effectively.
Learning objective: Players will experience dynamic risk scenarios and develop adaptability in the face of project uncertainties.
            	This objective is implemented through uncertainty-based decisions and scenario events. In sponsor management, selected sponsors may reject the offer, which forces the player to revise the financial plan. In emergency training, players prepare team members for various types of crises. During Festival Day, unexpected scenarios test whether the player made appropriate risk preparation decisions earlier in the game.

2.2.4. Monitor project performance using Gantt charts, key performance indicators (KPIs), and performance reports.
Learning objective: Players will track their progress and evaluate project outcomes based on time, budget, and quality indicators.
	This objective is implemented through visual feedback and performance indicators. Players can examine charts, scores, budget changes, expected attendance, and Gantt chart information during the game. The final performance report summarizes the project outcome in terms of time management, budget performance, scope adherence, event quality, and participant satisfaction.

2.2.5. Analyze how scope, resources, and schedule can be used to improve project outcomes and how changes in one affect the others.
Learning objective: Players will understand the relationships among project scope, schedule, and resources, and how each impacts the others.
            	This objective is implemented by connecting decisions across different project dimensions. For example, selecting more volunteers, vendors, or higher-quality equipment may improve event quality and scope, but it can also increase cost, electricity demand, space usage, or setup complexity. By reviewing the final report and replaying the game with different decisions, players can observe how changes in one area affect the overall project result.

2.2.6. Enhance teamwork, leadership/motivation, and communication skills during project execution.

Learning objective: Players will develop essential soft skills through managing teams, motivating team members, and maintaining clear communication.
	This objective is implemented through team-based activities and scenario-based challenges. At the beginning, players build a balanced team by considering attributes such as communication, teamwork, reliability, stress tolerance, and workload capacity. Later, they assign members to tasks and training programs. Festival Day scenarios also require coordinated responses, showing that project success depends not only on technical planning but also on effective team management.

## Realistic Constraints

The Festival Management Simulation was designed to reflect the main constraints that can be faced in a real project. In the game, the player cannot make decisions without considering limitations such as available resources, project duration, budget, and required festival scope. Each decision affects at least one of these constraints, creating a trade-off. For example, a high-quality option may increase participant satisfaction but also increase costs, while a cheaper option may protect the budget but reduce event quality. Therefore, these constraints are directly linked to the decision-making mechanisms and the player's final evaluation. The main realistic constraints of the project are explained under four categories: resource constraints, time constraints, budget constraints, and scope constraints.

### Resource Constraint

Resource constraint is one of the main realistic constraints in the Festival Management Simulation game. In a real festival project, the project manager cannot use unlimited people, equipment, or operational resources. Therefore, the game includes a limited number of team members, phones, and computers as project resources. These resources directly affect how activities can be assigned, scheduled, and completed.

At the beginning of the game, the player is provided with the baseline Gantt chart and the available number of phone and computer resources. In this way, the player can see not only the activity durations and precedence relationships, but also the resource limitations that may affect the schedule. This allows the player to consider resource availability before making scheduling and planning decisions.

The player also selects team members at the beginning of the game. In the resource-constrained logic, the most important team-related variable is workload capacity. Workload capacity determines how many activities a team member can be assigned to during the project. Therefore, the player cannot assign the same person to an unlimited number of activities. If a team member’s workload capacity is exceeded, the game treats this as a resource capacity violation, and the player must revise the assignment.

In addition to team workload capacity, some activities require phone and computer resources. Since multiple activities can be performed in parallel in the Gantt chart, resource conflicts may occur. For example, two or more activities may be scheduled at the same time, but the total number of required phones or computers may exceed the available resource capacity stated in the Project Charter. In this case, the game imposes a resource capacity constraint and does not allow all conflicting activities to proceed simultaneously.

To resolve these conflicts, the player chooses a resource leveling heuristic. This heuristic determines which activity should receive priority when parallel activities compete for the same limited resources. Possible heuristic options may include Minimum Duration First, Maximum Duration First, Minimum Slack First, Highest Resource Demand First, or Critical Activity First.

When a resource conflict occurs, the selected heuristic is used to decide which activity should be performed first. Activities that cannot receive the required resources are delayed or temporarily blocked until enough resources become available. For example, if two parallel activities require computers at the same time but the available computer capacity given in the Project Charter is not enough, the game checks the selected heuristic and gives priority to one of the activities. The other activity is postponed, which may affect the project schedule and the player’s time management performance.

The player can also purchase extra phones or computers if the current resource capacity is not enough. This option provides additional flexibility and can help prevent delays caused by resource shortages. However, buying extra resources increases project cost and reduces the remaining budget. Therefore, the player must compare the benefit of preventing schedule delays with the financial cost of purchasing additional resources.

This creates an important trade-off between resource availability, budget control, and time management. Buying extra resources may improve the schedule and reduce delays, but it can weaken budget performance. On the other hand, using only the existing resources may protect the budget, but it can cause some activities to be postponed under the selected heuristic.

Overall, the resource constraint helps the player understand that project scheduling is not only about arranging activities in time, but also about allocating limited resources efficiently. By reading the Project Charter, choosing a heuristic, deciding whether to buy extra resources, and observing the effect on the schedule and budget, the player experiences how different resource management strategies can lead to different project outcomes.

### Time Constraint

Time constraint is one of the main constraints in the Festival Management Simulation game. Since the festival has a fixed date, the player must complete the required preparations before the festival day. Therefore, the game is designed around a project schedule that includes activity durations, precedence relationships, and a Gantt chart structure.

At the beginning of the game, the player is provided with an example Gantt chart and the precedence relationships between activities. This allows the player to understand which activities can be performed in parallel and which activities must wait for the completion of previous activities. In this way, the player is expected to manage the project schedule by considering both activity durations and dependency relationships.

In the game logic, each activity has an expected duration. This expected duration represents the planned or recommended completion time for that activity. However, it does not mean that the activity automatically closes when the expected duration is reached. The player still controls the completion of activities through their decisions. Therefore, expected durations are used as benchmarks for evaluating time performance rather than strict time limits.

For example, if an activity has an expected duration of 4 weeks, it is expected to be completed within 4 weeks under normal conditions. If the player completes the activity within this expected time, it supports the time performance. If the player takes longer than expected, the activity can still be completed, but the extra time is treated as a delay. These delays may consume the available buffer time and reduce the time-related evaluation at the end of the game.

The expected project completion time is designed as 8 weeks. However, the festival day is set at the end of Week 10. This creates a 2-week buffer for the player. A player who completes the activities close to their expected durations can finish the project in approximately 8 weeks, leaving 2 weeks of flexibility before the festival day. This buffer is included to represent unexpected events, resource conflicts, activity delays, or decision revisions that may occur during project execution.

However, the buffer does not remove the importance of time management. Random in-game scenarios may change activity durations, reduce resource availability, or force the player to revise previous decisions. As a result, some activities may take longer than expected. If the player cannot manage these delays effectively and activities remain incomplete before the festival day, the time performance decreases.

At the end of the game, the time-related evaluation assesses whether the required activities were completed before the festival day and whether they were completed within their expected durations. Critical activities have a stronger effect because delays in these activities can directly affect the overall project schedule. In this way, the time constraint encourages the player to complete activities on time, use the buffer carefully, and prioritize important activities before the fixed festival deadline.

### Budget Constraint

Budget constraint is one of the most visible and important constraints in the game. The player starts with an initial festival budget of 400,000, and almost every major decision affects the remaining budget. Since the festival is designed as a non-profit student event, the player is expected to use the available budget efficiently while still maintaining event quality, participant satisfaction, and scope requirements.

In the game, financial inflows are intentionally limited to specific activities. The player can receive money only through Sponsor Management, Ticket Pricing Strategy, and Food Vendor Selection. Sponsor Management creates income through sponsor contributions. Ticket Pricing Strategy generates ticket revenue depending on the selected ticket price and expected attendance. Food Vendor Selection can also create income through vendor participation fees, rental payments, or contribution agreements. Apart from these three activities, the other activities do not generate direct income for the player. Instead, they mainly create costs or quality-related effects. For example, Promotion Strategy, Entertainment Line-Up, Stage Setup Choice, Sound System Choice, Decoration Theme Decision, Transport Coordination, and Cleaning and Security Team Decision mostly require spending from the available budget.

This structure makes the budget system more realistic because a festival project usually has limited income sources but many cost items. Therefore, the player cannot solve every problem by expecting money from all activities. The player must carefully manage the balance between incoming money and outgoing costs. For example, selecting a high-quality entertainment line-up may improve participant satisfaction, but it also increases cost. Similarly, choosing a better sound system, decoration theme, or stage setup may improve event quality but reduce the remaining budget.

The player is allowed to continue even if the budget becomes negative up to a certain limit. Specifically, the budget can decrease up to  -300,000. However, if the budget goes below -300,000, the project fails, and the game ends. This rule represents a realistic financial risk limit. In real projects, a limited deficit may be manageable, but exceeding the acceptable financial threshold can make the project financially unsustainable.

The festival's non-profit structure is also reflected in its end-of-game budget logic. The main aim of the festival is not to generate personal or organizational profit, but to organize a successful student event. Therefore, if there is remaining money at the end of the game, this amount is not treated as profit. Instead, it is transferred to a scholarship fund for future students. This gives the financial system a social purpose and makes the budget logic more consistent with the festival's educational and non-profit nature.

To make the budget system more realistic, costs and prices were not assigned completely randomly. In many activities, the price is connected to the efficiency, popularity, quality, or performance score of the selected alternative. For example, more efficient food vendors generally charge higher prices because they offer better service capacity and speed while incurring lower operational costs. Similarly, stage setup, sound system, decoration, and cleaning/security options have price ranges based on their performance levels.

Overall, the budget constraint was addressed by designing the game around a limited-income and multi-cost structure. The player must generate enough financial support through sponsors, ticket sales, and food vendors while controlling the costs of all other festival activities. The -300,000-failure threshold prevents unlimited overspending, while the scholarship fund rule gives a meaningful purpose to any remaining budget. Therefore, the budget system teaches the player how financial decisions affect a project's overall success, sustainability, and social responsibility.

### Scope Constraint

Scope constraint refers to the minimum project requirements that must be satisfied for the festival to be considered successful. In the game, the player is not only expected to stay within the budget and finish on time, but also to complete the essential festival components. Therefore, scope adherence is used as one of the main evaluation dimensions in the final scoring system.

The scope adherence system is based on specific requirements for different activities. Each requirement is checked as either satisfied or not satisfied. Then, the game calculates how many of these requirements are met by the player. In this way, scope performance is not evaluated only as a simple pass-or-fail condition. Instead, a scope adherence ratio is calculated to show the percentage of the required project scope completed by the player.

The seven scope requirements used in the game are listed below:

●       For the Team Assignment, the selected team must be balanced. This means the overall average team performance should exceed 2.5.

●       For Sponsor Management, the player must select at least 2 sponsors. In addition, the overall average sponsor score should exceed 2.5. Sponsor contributions are also considered, as sponsor selection is one of the game's limited sources of revenue.

●       For the Ticket Pricing Strategy, the player must meet the predefined minimum attendance target. This requirement checks whether the selected ticket pricing decision leads to sufficient festival participation.

●       For the Entertainment Line-Up, the overall average popularity level of selected artists should be above 3. In addition, the player must select at least 1 main headliner and at least 2 supporting artists. This ensures that the festival's entertainment structure is complete and attractive enough for participants.

●       For Volunteer / Club Recruitment, the player must include at least one activity from each of the required activity types: competitive, artistic, informational, and interactive. In addition, the player must select at least 2 volunteers and 3 clubs. This requirement ensures that the festival includes sufficient operational support and diversity of activities.

●       For Food Vendor Selection, the player must provide cuisine variety by selecting at least one vendor from each required cuisine type. Also, the overall average hygiene rating for the selected food vendors should be above 2.5. This ensures that the food vendor decision satisfies both diversity and safety expectations.

●       For Festival Cleaning and Security, the player must select at least 1 cleaning crew and at least 1 security team. This requirement is included because cleaning and security are essential for the safe and well-organized operation of the festival.

The scope adherence ratio can be calculated as follows:

This ratio is then used in the player's final evaluation. A higher scope-adherence ratio indicates that the player managed the festival as a more cohesive project. A lower ratio indicates that some essential project components were ignored or only partially completed. For example, a player may stay within budget and finish on time, but if the festival lacks sufficient sponsors, activity diversity, food variety, hygiene standards, or safety support, the project cannot be considered fully successful.

Therefore, the scope constraints ensure that the player does not focus solely on a single performance dimension, such as budget or time. Instead, the player is encouraged to manage the festival as a complete project by satisfying the minimum operational, financial, entertainment, safety, and participant-related requirements.

# METHODOLOGY

## Activity Network Diagram

The first step of the methodology was to define the festival preparation process as a project activity network. Since the aim of the game is to simulate project management decisions, the overall festival organization process was divided into distinct activities, each with specific durations and precedence relationships. This structure provides the foundation for the Gantt chart, Critical Path Method calculations,  and the time management scoring system.

The activity network starts with the Start node and ends with the Finish node. Between these two nodes, the main festival preparation activities are represented as project tasks. These activities include team assignments, initial festival layout planning, emergency plan training, sponsor management, promotion strategy, entertainment line-up, ticket pricing, volunteer and club recruitment, food vendor selection, stage setup, sound system selection, transport coordination, decoration theme decision, cleaning and security planning, and final facility layout mapping.

The network was designed by considering both real-life festival preparation logic and gameplay flexibility. In the earlier version of the Gantt chart, some activities related to strict precedence relationships, which made the project flow too rigid and reduced the player’s scheduling flexibility. Therefore, in the revised version, some unnecessary precedence constraints were reduced. Activities such as Promotion Strategy, Ticket Pricing Strategy, Volunteer/Club Recruitment, and Food Vendor Selection were shifted earlier in the schedule to reduce waiting times and create a smoother game flow.

However, not all precedence relationships were removed. Some dependencies were intentionally preserved to keep the project realistic. For example, Emergency Plan Training depends on both Team Assignment and Initial Festival Layout Mapping, because safety planning requires both the assigned team and basic layout information. Similarly, Ticket Pricing Strategy depends on Sponsor Management, as sponsor contributions affect the festival's financial structure. Volunteer/Club Recruitment depends on the promotion and entertainment decisions, as the number and types of volunteers and clubs should align with the planned festival content. Finally, Facility Layout Mapping is kept as a final integration activity because it combines the physical and operational decisions made in the previous activities.

Figure 1 shows the revised activity network used in the simulation. In the diagram, each node represents an activity, and each arrow represents a precedence relationship between two activities. The red nodes indicate critical activities with zero total slack, while the blue nodes indicate activities that have scheduling flexibility. This visual structure helps clarify which activities directly affect the project completion time and which can be delayed without immediately delaying the whole project.

Table 1 presents the activity durations and predecessor relationships used in the network. These values were used to calculate the earliest start, earliest finish, latest start, latest finish, total slack, and criticality status of each activity. The resulting project duration is 32-time units, which corresponds to 8 weeks in the game. Since the festival takes place at the end of the 10th week, which corresponds to the beginning of the 11th week, the player has a 2-week buffer after the planned project completion time.

Overall, the project activity network provides the structural basis of the game’s scheduling system. It allows the player to understand how activities are connected, which tasks can be performed in parallel, and which tasks are critical for completing the festival preparation on time. Therefore, the network is not only a planning tool but also an important learning mechanism that supports the educational purpose of the simulation

Figure 1. Revised Activity Network of the Festival Management Simulation

| No | Activity | Duration | Predecessor(s) |
| --- | --- | --- | --- |
| 1 | Team Assignment | 4 | Start |
| 2 | Initial Festival Layout Mapping | 4 | Start |
| 3 | Emergency Plan Training | 4 | Team Assignment, Initial Festival Layout Mapping |
| 4 | Sponsor Management | 8 | Team Assignment |
| 5 | Promotion Strategy | 8 | Emergency Plan Training |
| 6 | Entertainment Line-Up | 8 | Emergency Plan Training |
| 7 | Ticket Pricing Strategy | 4 | Sponsor Management |
| 8 | Volunteer/Club Recruitment | 8 | Promotion Strategy, Entertainment Line-Up |
| 9 | Food Vendor Selection | 8 | Ticket Pricing Strategy |
| 10 | Stage Setup Choices | 4 | Volunteer/Club Recruitment |
| 11 | Sound System Choices | 4 | Volunteer/Club Recruitment |
| 12 | Transport Coordination | 4 | Volunteer/Club Recruitment |
| 13 | Decoration Theme Decision | 2 | Volunteer/Club Recruitment |
| 14 | Festival Cleaning & Security | 4 | Volunteer/Club Recruitment |
| 15 | Facility Layout Mapping | 4 | Food Vendor Selection, Stage Setup Choices, Sound System Choices, Decoration Theme Decision, Festival Cleaning & Security |

Table 1. Activity Durations and Precedence Relationships

## CPM Analysis

After defining the activity durations and precedence relationships, the Critical Path Method was applied to evaluate the project schedule. The CPM analysis was used to calculate the earliest start, earliest finish, latest start, and latest finish for each activity, as well as the total slack and critical status. These values are presented in Table 2.

| Activity | Duration | ES | EF | LS | LF | Total Slack | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Start | 0 | 0 | 0 | 0 | 0 | 0 | Yes |
| Team Assignment | 4 | 0 | 4 | 0 | 4 | 0 | Yes |
| Initial Festival Layout Mapping | 4 | 0 | 4 | 0 | 4 | 0 | Yes |
| Sponsor Management | 8 | 4 | 12 | 8 | 16 | 4 | No |
| Emergency Plan Training | 4 | 4 | 8 | 4 | 8 | 0 | Yes |
| Ticket Pricing Strategy | 4 | 12 | 16 | 16 | 20 | 4 | No |
| Promotion Strategy | 8 | 8 | 16 | 8 | 16 | 0 | Yes |
| Entertainment Line-Up | 8 | 8 | 16 | 8 | 16 | 0 | Yes |
| Food Vendor Selection | 8 | 16 | 24 | 20 | 28 | 4 | No |
| Volunteer/Club Recruitment | 8 | 16 | 24 | 16 | 24 | 0 | Yes |
| Stage Setup Choices | 4 | 24 | 28 | 24 | 28 | 0 | Yes |
| Sound System Choices | 4 | 24 | 28 | 24 | 28 | 0 | Yes |
| Transport Coordination | 4 | 24 | 28 | 28 | 32 | 4 | No |
| Decoration Theme Decision | 2 | 24 | 26 | 26 | 28 | 2 | No |
| Festival Cleaning & Security | 4 | 24 | 28 | 24 | 28 | 0 | Yes |
| Facility Layout Mapping | 4 | 28 | 32 | 28 | 32 | 0 | Yes |
| Finish | 0 | 32 | 32 | 32 | 32 | 0 | Yes |

Table 2. CPM Results for the Revised Activity Network

The CPM results show that the total project duration is 32-time units, which corresponds to 8 weeks in the game schedule. The festival is planned for the end of the 10th week, which corresponds to the beginning of the 11th week. Therefore, the planned schedule provides a 2-week buffer period after the expected project completion time. This buffer gives the player limited flexibility to absorb possible delays before the festival day.

Since a delay in any critical activity may reduce the available buffer or delay the entire project, the critical path analysis is directly connected to the game’s time management system. The player must carefully manage critical activities while using the available flexibility in non-critical activities, such as Sponsor Management, Ticket Pricing Strategy, Food Vendor Selection, Transport Coordination, and Decoration Theme Decision.

## Scenario System

### In Game Scenarios

To make the simulation more realistic, the game includes randomly generated in-game scenarios that create uncertainty during project execution. These scenarios occur at the beginning of an activity, during the activity, or after the player makes a decision. Their main purpose is to make activity durations, resource availability, costs, and decision conditions less predictable. In this way, the game not only evaluates the player’s initial plan but also tests how well the player can adapt when unexpected events change the planned project flow.

These scenarios are especially important for creating unexpected time effects. Some events directly increase or decrease the duration of an activity, while others indirectly affect time by reducing available resources, limiting choices, or forcing the player to revise a previous decision. Therefore, the player cannot assume that every activity will always follow its expected duration. Instead, the project schedule becomes dynamic, and the player needs to manage uncertainty, as in a real project environment.

At the beginning of the Team Assignment activity, the player may receive a message from the school administration stating that some students are assigned to other school events. In the game, the player normally has 15 possible team member options. When this scenario occurs, 3 randomly selected team members become unavailable, so the player continues the activity with 12 available options. This reduces the player’s flexibility while forming the project team and may create future time pressure because fewer available members can make task assignment and workload balancing harder.

In another possible Team Assignment scenario, two randomly selected team members may inform the player that they do not have exams during that period and can take responsibility for one additional task. As a result, only these 2 team members receive an increase in workload capacity. This creates a positive resource effect because the player can assign more work to these specific members. Since workload capacity affects how activities can be distributed among team members, this scenario can also reduce possible delays and support better time management.

For Emergency Plan Training, unexpected school regulations may affect the player’s choices. At the beginning of the activity, the school administration may announce that two randomly selected emergency training programs are mandatory. This limits the player’s freedom of choice and may increase the planned activity duration or cost depending on the required training options. Another possible scenario comes from the training company. The company may inform the player that one randomly selected training can be completed faster than expected. In this case, the duration of that training decreases by 1 time unit, creating a positive time effect on the project schedule.

In Sponsor Management, uncertainty is represented through the negotiation process. Even if the player selects a sponsor, the sponsor may reject the negotiation offer. However, the player has a limited number of trial rights during this activity. This means that if a selected sponsor rejects the offer, the player can try to negotiate with another sponsor until the trial limit is reached. This creates uncertainty because the player may still fail to secure sufficient sponsor support if the negotiation attempts are unsuccessful. As a result, Sponsor Management affects both Budget Control and Time Management, since rejected negotiations can reduce expected income and force the player to spend additional attempts adjusting sponsor decisions.

During Ticket Pricing Strategy, the player may receive a message from a team member stating that a rival university will organize a free festival on the same day. This scenario reduces ticket demand or attendance reliability because some potential participants may prefer attending the rival university’s festival instead. As a result, the player may need to reconsider the ticket pricing decision. Although this scenario primarily affects attendance and Event Quality, it also introduces decision uncertainty, as the player must respond to new market conditions.

In the Entertainment Line-up activity, the game can create both positive and negative unexpected situations. At the beginning of this activity, the player normally chooses from 3 main headliner options and 5 supporting artist options. In one scenario, the team works very effectively and finds additional artist alternatives. As a result, one extra main headliner option and one extra supporting artist option are added to the selection pool. Therefore, the available options increase to 4 main headliner options and 6 supporting artist options. This gives the player more alternatives and may improve Participant Satisfaction or Event Quality.

In another Entertainment Line-up scenario, after the player makes the entertainment decision, one of the selected supporting artists is randomly chosen and announces they cannot attend due to a scheduling conflict. The player can either select another supporting artist or continue without replacing that artist. This creates uncertainty after the decision has already been made and may force the player to spend additional time revising the entertainment plan. If the player continues without replacing the artist, satisfaction, attendance, or scope performance may decrease.

For Volunteer/Club Recruitment, the player typically chooses from 9 club options and 6 volunteer options. However, the number of available options may change due to randomly generated in-game scenarios. In a positive scenario, the festival receives more attention from students, and more clubs want to participate. As a result, 2 additional club options are added to the selection pool. Therefore, the number of available club options increases from 9 to 11, giving the player more flexibility and potentially improving activity variety and participant engagement.

A negative scenario can also occur. For example, the festival may overlap with the exam period, making 2 randomly selected clubs unavailable. In this case, the number of available club options decreases from 9 to 7. These clubs are removed randomly from the selection pool, so the player cannot know in advance which options will be lost. This reduces the player’s flexibility and may make it harder to cover all required activity types. As a result, the player may need to revise the volunteer/club recruitment decision and adapt to the new limitations.

In Food Vendor Selection, the available area may change because of school safety rules. At the beginning of the activity, the school may send an information message stating that occupational safety regulations require a reduction in the maximum vendor area. The maximum available square meter value is then reduced by a random amount between 40 and 70 m². This limits the number or type of vendors that can be selected and makes layout and capacity planning more difficult. Since the player may need to reconsider vendor choices, this scenario also creates indirect time uncertainty.

For Stage Setup Choice, the scenario system creates budget uncertainty that can also affect project decisions. In a negative scenario, an exchange rate increase causes all stage setup options to become 15% more expensive. This increases the cost of the selected stage option and can reduce Budget Control. In a positive scenario, the school decides to support the festival organization, and stage setup prices decrease by 15%. This reduces financial pressure and gives the player more flexibility in later decisions.

For Decoration Theme Decision, the selected main headliner may create an unexpected constraint. The artist may request that one specific decoration theme not be used. In this case, that decoration theme becomes unavailable for selection, although the player can still see it on the decision screen. This limits the player’s options and may force the player to revise the decoration decision. Therefore, it creates uncertainty in both decision-making and possible activity planning.

In Festival Cleaning & Security, the player normally has a 100 m² footprint area limit. However, the school may change this limit due to operational reasons. When this scenario occurs, the available footprint area is randomly increased or decreased by 10 m², 20 m², or 30 m². For example, the limit may decrease from 100 m² to 90, 80, or 70 m², or it may increase to 110, 120, or 130 m². This creates uncertainty in cleaning and security planning because the player may need to adapt the selected options according to the new area limitations. If the available footprint decreases, the player has less flexibility and may need to choose smaller or fewer options. If it increases, the player gains more flexibility in selection and layout planning.

Finally, during Final Layout Mapping, two randomly selected facilities, such as food vendors, club stands, or volunteer stands, may reject their initially assigned location. When the player places one of these facilities in that area, a warning message appears stating that the selected facility does not want to be located there and requests a different location. The player must then revise the layout and place the facility somewhere else. This scenario creates uncertainty at the final planning stage and may increase the time needed to complete the layout.

Overall, these random scenarios are not separate scoring categories. Instead, they modify the conditions of existing activities and indirectly affect scores such as Time Management, Budget Control, Event Quality, Participant Satisfaction, and Scope Adherence. By creating unexpected changes in duration, resources, costs, and decision options, the scenario system makes the game more dynamic and realistic. The player must not only create an initial plan but also adapt it when unexpected project events occur.

### Festival Day Scenarios

      - Overview

Festival Day takes place during the execution phase of the project and tests how well the player's previous planning, emergency training, and resource allocation decisions support real-time problem solving. During Festival Day, unexpected scenarios appear randomly. Since not all scenarios occur at the same time, the player must decide how many available trained team members should be assigned to each scenario when it appears.

Festival Day lasts 4 minutes in total. Therefore, all scenario durations are expressed in minutes and kept short. The system is designed to make resource allocation meaningful. Assigning fewer members does not immediately make the task impossible, but it increases the actual completion time and may cause the scenario to fail if there is not enough time left during Festival Day.

Each scenario has three main parameters: Required Members, Base Time, and Max Allowed Time. Required Members shows how many trained members are needed to complete the scenario in its base time. Base Time represents the ideal completion time when the required number of trained members is assigned. Max Allowed Time represents the maximum time that the scenario can take under normal conditions.

The required number of members is determined according to the size and complexity of the scenario. Small individual issues require 1 trained member, medium operational problems require 2 trained members, and larger multi-location or multi-person incidents require 3 trained members. Since the scenarios appear randomly and not all at once, assigning 3 members to larger scenarios is feasible within the total team size.

      - General Calculation Logic

The actual completion time depends on how many trained members the player assigns to the scenario. If the player assigns the required number of members, the scenario is completed in its base time. If fewer trained members are assigned, the actual completion time increases proportionally.

Actual Time = Base Time x Required Members / Assigned Members

If no trained member is assigned, the task cannot be completed.

If Assigned Members = 0, Task Completion = 0

Since Festival Day has a fixed total duration of 4 minutes, each scenario must also be completed within the remaining Festival Day time. Therefore, Task Completion depends not only on the scenario's own maximum allowed time, but also on the time remaining when the scenario appears.

Task Completion = 1 if Assigned Members > 0 and Actual Time <= min(Max Allowed Time, Remaining Festival Time)

Otherwise, Task Completion = 0

This means that even if the scenario could normally be completed within its own allowed time, it still fails if there is not enough Festival Day time left.

After Task Completion is determined, the player's response speed is calculated.

Response Speed = Base Time / Actual Time

If the player assigns the required number of members, Actual Time equals Base Time, so Response Speed becomes 1. If fewer members are assigned, Actual Time increases and Response Speed decreases.

Scenario Score = Task Completion x Response Speed

If the task is not completed, Task Completion becomes 0 and the scenario score becomes 0. If the task is completed, the player receives a score based on how efficiently the scenario was handled.

| Variable | Definition |
| --- | --- |
| Base Time | The ideal completion time of the scenario when the player assigns the full required number of trained members. |
| Required Members | The number of trained members needed to complete the scenario in its base time. |
| Assigned Members | The number of trained members the player actually assigns to the scenario. |
| Actual Time | The calculated time needed to complete the scenario based on the number of assigned members. |
| Max Allowed Time | The maximum time the scenario is allowed to take under normal conditions. |
| Remaining Festival Time | The amount of time left from the total 4 minute Festival Day when the scenario appears. |
| Task Completion | A binary value showing whether the scenario is successfully completed. It can only be 0 or 1. |
| Response Speed | A performance value showing how close the player’s response time is to the ideal base time. |
| Scenario Score | The final score of an individual scenario. It depends on whether the task is completed and how fast it is completed. |

Table 4 : Definition of the Variables

      - Scenario Parameters

| Scenario | Required Members | Base Time | Max Allowed Time |
| --- | --- | --- | --- |
| Main Stage Power Outage | 2 | 0.67 min | 1.33 min |
| Food Vendor Power Failure | 3 | 0.75 min | 2.25 min |
| Overcrowding Near Main Stage | 2 | 0.58 min | 1.17 min |
| Partial Area Evacuation | 3 | 0.83 min | 2.50 min |
| Participant Collapse | 1 | 0.50 min | 1.00 min |
| Multiple Minor Injuries | 3 | 0.92 min | 2.75 min |
| VIP Complaint | 1 | 0.58 min | 1.00 min |
| Weather Disruption | 3 | 1.00 min | 3.00 min |

Table 5: Detailed Scenario Parameters

      - Detailed Scenario Calculations

Scenario 1: Main Stage Power Outage

During the main performance, the main stage suddenly loses power, causing the sound system and lights to stop. The player must assign trained members quickly to restore power and prevent crowd frustration from escalating.

·       Required Members: 2

·       Base Time: 0.67 min

·       Max Allowed Time: 1.33 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 1.33 min | Completed if remaining time >= 1.33 min | 0.50 |
| 2 | 0.67 min | Completed if remaining time >= 0.67 min | 1.00 |

Table 6: Scenario 1 Member Based Time and Score Tables

Scenario 2: Food Vendor Power Failure

Several food vendors lose electricity during peak service time, causing food preparation and sales to stop. The player must respond by assigning trained members to restore vendor operations and reduce service delays.

·       Required Members: 3

·       Base Time: 0.75 min

·       Max Allowed Time: 2.25 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 2.25 min | Completed if remaining time >= 2.25 min | 0.33 |
| 2 | 1.13 min | Completed if remaining time >= 1.13 min | 0.67 |
| 3 | 0.75 min | Completed if remaining time >= 0.75 min | 1.00 |

Table 7: Scenario 2 Member Based Time and Score Tables

Scenario 3: Overcrowding Near Main Stage

A large number of participants gather near the main stage, creating unsafe crowd density and movement problems. The player must assign trained members to control the crowd, redirect people, and restore safe circulation.

·       Required Members: 2

·       Base Time: 0.58 min

·       Max Allowed Time: 1.17 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 1.17 min | Completed if remaining time >= 1.17 min | 0.50 |
| 2 | 0.58 min | Completed if remaining time >= 0.58 min | 1.00 |

Table 8: Scenario 3 Member Based Time and Score Tables

Scenario 4: Partial Area Evacuation

A specific zone in the festival area must be evacuated due to an unexpected issue. The player must assign trained members to guide participants safely and complete the evacuation before panic or delays occur.

·       Required Members: 3

·       Base Time: 0.83 min

·       Max Allowed Time: 2.50 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 2.50 min | Completed if remaining time >= 2.50 min | 0.33 |
| 2 | 1.25 min | Completed if remaining time >= 1.25 min | 0.67 |
| 3 | 0.83 min | Completed if remaining time >= 0.83 min | 1.00 |

Table 9: Scenario 4 Member Based Time and Score Tables

Scenario 5: Participant Collapse

A participant collapses in the crowd due to exhaustion or a medical issue. The player must assign a trained member immediately to provide first response and stabilize the situation.

·       Required Members: 1

·       Base Time: 0.50 min

·       Max Allowed Time: 1.00 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 0.50 min | Completed if remaining time >= 0.50 min | 1.00 |

Table 10: Scenario 5 Member Based Time and Score Tables

Scenario 6: Multiple Minor Injuries

Several participants experience minor injuries such as slips, falls, or small accidents during the festival. The player must assign trained members to handle multiple cases efficiently and prevent medical response delays.

·       Required Members: 3

·       Base Time: 0.92 min

·       Max Allowed Time: 2.75 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 2.75 min | Completed if remaining time >= 2.75 min | 0.33 |
| 2 | 1.38 min | Completed if remaining time >= 1.38 min | 0.67 |
| 3 | 0.92 min | Completed if remaining time >= 0.92 min | 1.00 |

Table 11: Scenario 6 Member Based Time and Score Tables

Scenario 7: VIP Complaint

A sponsor or VIP guest reports a serious issue related to access, service quality, or unmet expectations. The player must assign a trained member to communicate with the guest and resolve the complaint before it damages the festival’s reputation.

·       Required Members: 1

·       Base Time: 0.58 min

·       Max Allowed Time: 1.00 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 0.58 min | Completed if remaining time >= 0.58 min | 1.00 |

Table 12: Scenario 7 Member Based Time and Score Tables

Scenario 8: Weather Disruption

Sudden weather changes, such as heavy rain, disrupt parts of the festival area and affect participant movement. The player must assign trained members to reorganize affected areas and keep the festival operating smoothly.

·       Required Members: 3

·       Base Time: 1.00 min

·       Max Allowed Time: 3.00 min

| Assigned Members | Actual Time | Task Completion Condition | Scenario Score |
| --- | --- | --- | --- |
| 0 | Failed | No member assigned | 0 |
| 1 | 3.00 min | Completed if remaining time >= 3.00 min | 0.33 |
| 2 | 1.50 min | Completed if remaining time >= 1.50 min | 0.67 |
| 3 | 1.00 min | Completed if remaining time >= 1.00 min | 1.00 |

Table 13: Scenario 8 Member Based Time and Score Tables

Scenario 9: Team Management Scenario

In addition to operational Festival Day scenarios, the game includes a team management scenario to evaluate the player’s leadership, motivation management, and coordination skills. During Festival Day, the team may experience fatigue, stress, and communication problems due to continuous operations and unexpected situations. If the project manager does not respond properly, team motivation may decrease and future scenario performance may be negatively affected.

Unlike the other Festival Day scenarios, this scenario is not based on assigning trained members. Instead, the player chooses one management action to improve team motivation and stabilize team coordination. Since Festival Day lasts only 4 minutes, each management decision also has an actual time and must fit within the remaining Festival Day time.

| Decision Option | Description | Actual Time |
| --- | --- | --- |
| Quick Team Meeting | Clarifies responsibilities and improves communication. | 0.50 min |
| Provide Incentives | Increases motivation through rewards or recognition. | 0.25 min |
| Reorganize Task Distribution | Balances workload among team members. | 0.75 min |
| No Action | No intervention is made, so motivation may continue to decrease. | 0.00 min |

Table 14 : Decision Options for Scenario 9 with Descriptions

The selected management action can only be applied if its actual time fits within the remaining Festival Day time.

Decision Completion = 1 if Actual Time <= Remaining Festival Time

Otherwise, Decision Completion = 0

If Decision Completion = 0, the selected action cannot be completed in time and the Team Management Scenario Score becomes 0.

The Team Management Scenario Score is calculated using four factors: Decision Completion, Decision Quality, Motivation Impact, and Operational Stability.

Team Management Scenario Score = Decision Completion x [(Decision Quality x 0.40) + (Motivation Impact x 0.35) + (Operational Stability x 0.25)]

| Variable | Definition |
| --- | --- |
| Decision Completion | Shows whether the selected action can be completed within the remaining Festival Day time. |
| Decision Quality | Shows how appropriate the selected action is for the situation. |
| Motivation Impact | Shows how much the selected action improves or protects team motivation. |
| Operational Stability | Shows how well the selected action supports continued festival operations. |

Table 15 : Scenario 9 Score Variables with Definition

| Decision Option | Actual Time | Decision Quality | Motivation Impact | Operational Stability | Final Score |
| --- | --- | --- | --- | --- | --- |
| Quick Team Meeting | 0.50 min | 0.90 | 0.80 | 0.85 | 0.85 |
| Provide Incentives | 0.25 min | 0.80 | 0.95 | 0.75 | 0.84 |
| Reorganize Task Distribution | 0.75 min | 0.85 | 0.75 | 0.90 | 0.83 |
| No Action | 0.00 min | 0.20 | 0.10 | 0.30 | 0.19 |

Table 16 :Detailed Score Values for Scenario 9 Decision Options

The final score values in the table apply only if the selected action fits within the remaining Festival Day time. If the remaining time is less than the action’s actual time, Decision Completion = 0, and the final score becomes 0.

For example, if only 0.40 min remains and the player selects Quick Team Meeting, the action cannot be completed because it requires 0.50 min. Therefore, the Team Management Scenario Score becomes 0.

This scenario allows the game to evaluate the project manager’s soft skills, especially leadership, motivation control, and team coordination under pressure, while still keeping the 4 minute Festival Day time constraint consistent with the other scenarios. Its final score is normalized between 0 and 1, so it can be included in the overall Festival Day scenario score together with the other triggered scenarios.

      - Overall Festival Day Scenario Score

Since multiple scenarios may appear randomly during Festival Day, the game also calculates one combined Festival Day Scenario Score at the end of the execution phase. This score represents the player's overall crisis management performance during Festival Day.

Each triggered scenario is first scored individually using the same formula:

Scenario Score = Task Completion x Response Speed

Then, all triggered scenario scores are combined into a single overall score by calculating their average.

Overall Festival Day Scenario Score = Sum of Scenario Scores / Number of Triggered Scenarios

Overall Festival Day Scenario Score = (S1 + S2 + S3 + ... + Sn) / n

| Symbol | Meaning |
| --- | --- |
| Si | Score of triggered scenario i |
| n | Number of scenarios triggered during Festival Day |

Table 17 : Meaning of the Symbols

Only triggered scenarios are included in the calculation. Scenarios that do not appear during Festival Day are not included, because the player should not be penalized for events that were not triggered. Failed scenarios receive a score of 0, so they reduce the overall Festival Day Scenario Score.

## Feedback Page

After the festival day is completed, the game presents the player with a final feedback evaluation page. This page functions as the closing result screen of the simulation and shows the main scores achieved by the player based on their decisions throughout the game. Instead of only giving a single final score, the feedback page separates the result into different evaluation areas so that the player can understand which parts of the project were successful and which parts need improvement.

For Participant Satisfaction, if 4 out of 4 satisfaction requirements are met, the output is Excellent. If 3 out of 4 requirements are met, the output is Good. If 2 out of 4 requirements are met, the output is Moderate. If 1 out of 4 requirements is met, the output is Weak. If 0 out of 4 requirements are met, the output is Very Low. The evaluated satisfaction parameters are Entertainment Line-up, Volunteer / Club Recruitment, Sound System Choice, and Decoration Theme Decision.

For Event Quality, if the total estimated attendance is 5000 or above, the output is Excellent — Target Exceeded. If the attendance is between 4000 and 4999, the output is Good but Below Target. If the attendance is between 2500 and 3999, the output is Moderate. If the attendance is between 1000 and 2499, the output is Weak. If the attendance is between 0 and 999, the output is Very Low.

For Scope Adherence, if 12 out of 12 scope requirements are met, the output is Excellent — Full Scope Completed. If 10–11 out of 12 requirements are met, the output is Good — Minor Scope Gaps. If 6–9 out of 12 requirements are met, the output is Moderate — Partial Scope Completion. If 3–5 out of 12 requirements are met, the output is Weak — Major Scope Gaps. If 0–2 out of 12 requirements are met, the output is Very Low — Scope Not Completed. The evaluated scope parameters are Team Assignment, Sponsor Management, Ticket Pricing Strategy, Entertainment Line-up, Volunteer / Club Recruitment, Food Vendor Selection, and Festival Cleaning & Security.

For Budget Control, if the final budget is 400,000 TL or higher, the output is Excellent — Budget Surplus. If the final budget is between 200,000 TL and 399,999 TL, the output is Strong Budget Control. If the final budget is between 0 TL and 199,999 TL, the output is Acceptable but Limited Budget. If the final budget is between -1 TL and -149,999 TL, the output is Risky Budget Performance. If the final budget is between -150,000 TL and -299,999 TL, the output is Critical Budget Performance. If the final budget is -300,000 TL or lower, the output is Budget Failure.

For Sponsor Management income, if the sponsor income is below 200,000 TL, the output is Weak Sponsor Income. If it is between 200,000 TL and 299,999 TL, the output is Moderate Sponsor Income. If it is 300,000 TL or above, the output is Strong Sponsor Income.

For Ticket Pricing revenue, if the ticket revenue is below 75,000 TL, the output is Weak Ticket Revenue. If it is between 75,000 TL and 149,999 TL, the output is Moderate Ticket Revenue. If it is 150,000 TL or above, the output is Strong Ticket Revenue.

For Food Vendor Selection income, if the vendor income is below 160,000 TL, the output is Weak Vendor Income. If it is between 160,000 TL and 299,999 TL, the output is Moderate Vendor Income. If it is 300,000 TL or above, the output is Strong Vendor Income.

For Promotion Strategy cost, if the promotion cost is below 25,000 TL, the output is Low Promotion Cost. If it is between 25,000 TL and 39,999 TL, the output is Moderate Promotion Cost. If it is 40,000 TL or above, the output is High Promotion Cost.

For Entertainment Line-up cost, if the entertainment cost is below 180,000 TL, the output is Low Entertainment Cost. If it is between 180,000 TL and 299,999 TL, the output is Moderate Entertainment Cost. If it is 300,000 TL or above, the output is High Entertainment Cost.

For Stage Setup cost, if the stage cost is below 140,000 TL, the output is Low Stage Cost. If it is between 140,000 TL and 199,999 TL, the output is Moderate Stage Cost. If it is 200,000 TL or above, the output is High Stage Cost.

For Sound System Choice cost, if the sound system cost is below 100,000 TL, the output is Low Sound Cost. If it is between 100,000 TL and 129,999 TL, the output is Moderate Sound Cost. If it is 130,000 TL or above, the output is High Sound Cost.

For Decoration Theme Decision cost, if the decoration cost is below 100,000 TL, the output is Low Decoration Cost. If it is between 100,000 TL and 129,999 TL, the output is Moderate Decoration Cost. If it is 130,000 TL or above, the output is High Decoration Cost.

For Festival Cleaning & Security cost, if the cleaning and security cost is below 50,000 TL, the output is Low Cleaning/Security Cost. If it is between 50,000 TL and 69,999 TL, the output is Moderate Cleaning/Security Cost. If it is 70,000 TL or above, the output is High Cleaning/Security Cost.

For Emergency Plan Training cost, if the training cost is below 30,000 TL, the output is Low Emergency Training Cost. If it is between 30,000 TL and 59,999 TL, the output is Moderate Emergency Training Cost. If it is 60,000 TL or above, the output is High Emergency Training Cost.

For Time Management, the output is determined by comparing each activity’s actual completion duration with its expected duration. If an activity is completed within the expected duration or earlier, the activity receives 100% of its point value. In this case, a critical activity contributes 8 points, and a non-critical activity contributes 4 points. If the delay is up to 25% of the expected duration, the output is Completed with a Small Delay. The score multiplier is 80%, so a critical activity contributes 6.4 points, and a non-critical activity contributes 3.2 points. If the delay is between 25% and 50% of the expected duration, the output is Completed with a Moderate Delay. The score multiplier is 60%, so a critical activity contributes 4.8 points, and a non-critical activity contributes 2.4 points. If the delay is between 50% and 100% of the expected duration, the output is Completed with a Major Delay. The score multiplier is 40%, so a critical activity contributes 3.2 points, and a non-critical activity contributes 1.6 points. If the delay is more than 100% of the expected duration but the activity is still completed before the festival day, the output is Completed Very Late. The score multiplier is 20%, so a critical activity contributes 1.6 points, and a non-critical activity contributes 0.8 points.If the activity is not completed before the festival day, the output is Not Completed Before Festival Day. The score multiplier is 0%, so both critical and non-critical activities contribute 0 points.

For Scenario Preparedness, if the score is in a high range, the output is Good or Excellent, depending on the final score. If the score is in the middle range, the output is Moderate. If the score is in a low range, the output is Weak. This parameter evaluates how prepared the player was for unexpected festival-day events such as power outages, medical emergencies, or other operational problems.

Overall, the final feedback evaluation page gives a separate result output for each parameter after the festival day is completed. By using these predefined score and value ranges, the game clearly shows the player which areas were successful, which areas were risky, and which areas need improvement in future playthroughs.

## Decision Mechanism and Scoring System

The decision mechanism and scoring system were designed to transform the festival preparation process into an interactive project management simulation. In each activity, the player is required to make decisions among several alternatives. These alternatives differ in terms of cost, quality, capacity, efficiency, popularity, safety, space requirement, electricity requirement, or participant satisfaction impact. Therefore, the player cannot make decisions based on only one factor. Instead, each decision creates a trade-off between budget, time, scope, participant satisfaction, and event quality.

The decision tables were created to support realistic and balanced gameplay. The values in these tables were not assigned completely randomly. Instead, they were designed by considering reasonable value ranges, activity requirements, and gameplay balance. The aim was to prevent the player from always reaching a successful outcome through random choices, while still allowing better results through strategic decision-making. For this reason, several activity datasets were checked with probability-based balancing. For example, randomly selected teams, sponsors, volunteers/clubs, and food vendors were tested to make sure that high-performance combinations are possible but not guaranteed. The detailed table values and balancing logic are provided in Appendix B.

The decision mechanism also includes physical and operational constraints. For example, some alternatives require more space, electricity, time, or operational support. Food vendors are evaluated not only on cost but also on service capacity, speed, hygiene rating, electricity requirements, and space requirements. Similarly, volunteer and club alternatives are evaluated based on their activity type, engagement level, and space requirements. These constraints make the game more closely resemble a real festival-planning problem, where decisions must be feasible both financially and operationally.

Price values were also determined systematically. In most activities, the price of an alternative is related to its performance, efficiency, popularity, or quality level. In general, higher-performing alternatives are placed closer to the upper price range, while lower-performing alternatives are placed closer to the lower price range. However, random variation was added to prevent the dataset from looking completely linear or artificial. This creates a more realistic market-like structure, where better alternatives are usually more expensive but not always in a perfectly predictable way. The detailed price formulas, minimum and maximum price ranges, and random variation values are presented in Appendix B.

For example, in the Food Vendor Selection activity, vendor efficiency is based on service capacity, speed, electricity requirement, and space requirement. A vendor that serves more participants faster while requiring less electricity and space is considered more efficient. Therefore, more efficient vendors generally have higher prices. However, because random variation is included, the player still needs to compare the alternatives carefully instead of selecting only based on price. Similar price determination logic was used for sponsor management, promotion strategy, stage setup, sound system, decoration theme, and cleaning/security decisions. The entertainment line-up cost structure was designed separately because the artist cost is mainly related to the popularity level and the artist type.

The scoring system evaluates the player’s project performance through several KPIs rather than calculating a single overall score. These KPIs are Budget Control, Time Management, Scope Adherence, Participant Satisfaction, and Event Quality. The detailed scoring logic for the KPI ‘s are provided in Appendix C.  Each KPI represents a different dimension of project success, and each one is interpreted separately in the final evaluation section. This structure was preferred because project performance cannot always be represented accurately with one combined score. For example, a player may manage the budget successfully but have low participant satisfaction, or may complete the project on time while failing to satisfy some scope requirements.

Scope Adherence measures whether the player satisfies the minimum requirements of the festival project. These requirements include forming a balanced team, selecting enough sponsors, reaching the attendance target, choosing the required entertainment structure, providing enough volunteer/club diversity, ensuring food variety and hygiene, and selecting cleaning and security teams. Instead of evaluating scope as only pass or fail, the game calculates a scope adherence ratio based on how many requirements are satisfied. The full list of scope criteria and thresholds is provided in Appendix D.

Participant Satisfaction evaluates the expected experience of festival participants. It is mainly affected by the entertainment popularity, volunteer/club engagement, sound system quality, and decoration theme. If the selected alternatives satisfy the required satisfaction conditions, they contribute positively to the participant satisfaction evaluation. The detailed satisfaction scoring conditions are provided in Appendix E.

Event Quality measures the technical and operational quality of the festival. It is affected by ticket pricing, promotion effectiveness, expected crowd appeal, volunteer/club diversity, sound system, stage setup, transport coordination, and cleaning/security decisions. This KPI reflects whether the festival is not only completed but also organized to an acceptable standard.

Budget Control evaluates how effectively the player manages the initial festival budget. The game starts with an initial budget of 400,000. The player can receive money only from Sponsor Management, Ticket Pricing Strategy, and Food Vendor Selection. Other activities mainly create costs or quality-related effects. The player is allowed to continue until the budget decreases to -300,000. If the budget goes below this threshold, the project fails. Since the festival is a non-profit student event, any remaining funds at the end of the game are transferred to a scholarship fund rather than treated as profit.

Time Management evaluates how well the player manages activity durations and the overall project schedule. The Time Management score is calculated on a 100-point scale and assesses whether the player completes project activities before the fixed festival day. In this logic, the score depends not only on the number of completed activities but also on the importance of those activities in the project schedule. Critical activities have a stronger effect on the score because delays in these activities can directly affect the overall project completion time. Non-critical activities also affect the score, but their impact is lower because they have more schedule flexibility. Therefore, critical activities are assigned higher point values than non-critical activities, while the total score is balanced to remain within 100 points. If an activity is completed on time or earlier than its expected duration, the player receives the full point value of that activity. If the activity is completed after its expected duration, the player still receives partial points depending on the delay level. If the activity is not completed before the festival day, it receives zero points. In this way, the Time Management score evaluates both activity completion and schedule discipline, while encouraging the player to prioritize important activities before the deadline. The detailed point distribution and delay-based calculation logic are provided in Appendix F.

As mentioned above, at the end of the game, these KPIs are not combined into one overall score. Instead, each KPI is shown and interpreted separately. The main aim of this system is not to make players compete with each other, but to help them learn from their own decisions. This allows players to better understand the strengths and weaknesses of their project management choices. For example, a player may learn that they managed the budget successfully but reduced Event Quality by choosing low-cost alternatives. Another player may create a high-quality festival but face financial risk due to costly decisions. In this way, the scoring system supports the game's educational purpose by showing that successful project management requires balancing multiple performance dimensions simultaneously.

## Godot Engine Implementation

The Project Management Simulation Game (PMSG) is implemented in Godot as an interactive, software-based educational simulation. The game allows the player to experience the full lifecycle of a project by taking the role of a project manager responsible for organizing a university festival. The implementation is structured around time, budget, scope, resource allocation, activity dependencies, and decision-based scoring.

At the beginning of the game, the player is first introduced to the gameplay through a detailed video tutorial. This tutorial explains the general flow of the game, how the player interacts with the interface, how decisions are made, and how performance is evaluated. After the tutorial, the player receives an official briefing in the form of an email from the university rectorate. This email provides the narrative context of the simulation and explains that the player is responsible for planning and executing the university festival within the given constraints.

Following the introductory email, the player is directed to the Project Charter screen. The Project Charter presents the main project objectives, constraints, success criteria, timeline, initial budget, and general calculation logic used in the game. It also explains the conditions that the player must satisfy throughout the simulation, such as completing the festival within the planned timeline, staying within budget limits, and meeting required scope criteria. The player must review and accept these conditions before the game officially begins.

Once the Project Charter is accepted, the game timer starts and the main simulation begins. From this point onward, the player can continuously monitor the remaining time, current budget, and project progress. These values are updated dynamically according to the player’s decisions.

Activity-Based Game Flow

The game is designed around a sequence of project management activities. Each activity is implemented as a separate panel or screen in Godot. Before starting an activity, the player is provided with a short activity manual that explains the purpose of the activity, the basic rules, and the expected decision logic. During gameplay, these manuals remain accessible so that the player can refer to them when needed.

The activities are not fully available from the beginning. Instead, they are unlocked according to a dependency-based structure. This means that some activities can only be opened after prerequisite activities are completed. For example, the player must first complete team selection before assigning team members to tasks. Similarly, final layout planning becomes meaningful only after the player has selected vendors, volunteers, sponsors, stage setup, sound system, cleaning and security teams. This structure reflects real project management logic, where certain tasks depend on the completion of previous steps.

The main activities include team assignment, work assignment, initial layout planning, emergency training, sponsor management, entertainment lineup selection, promotion strategy, ticket pricing, volunteer and club recruitment, food vendor selection, stage setup, sound system selection, transport coordination, decoration theme selection, cleaning and security planning, final facility layout mapping, and Festival Day scenarios. Each activity focuses on a different project management topic and affects later stages of the game through shared variables.

Decision and Dependency Mechanism

The implementation uses a decision-based system where each player choice updates the overall game state. For example, selecting sponsors changes the available budget, choosing artists affects expected attendance and satisfaction, selecting food vendors influences service capacity and event quality, and assigning emergency training affects scenario performance during Festival Day. In this way, decisions are interconnected rather than independent.

The dependency mechanism is one of the core parts of the implementation. Activities are controlled through status conditions such as locked, available, completed, or expired. An activity remains locked until its required previous activities are completed. Once the requirements are satisfied, the activity becomes available. After the player completes the activity, its status changes to completed and related future activities may become unlocked. If the player exceeds the planned time window, some activities may be treated as delayed or outside the original project scope.

The implementation integrates the CPM (Critical Path Method) into the activity dependency structure. Activities are connected through prerequisite relationships, and the project schedule is organized according to these dependencies. Based on the dependency network, critical activities that directly affect the overall project completion time are identified and prioritized within the gameplay flow. This allows the system to simulate realistic project sequencing and demonstrates how delays in critical activities can impact the entire project schedule. The CPM-based structure also supports the week-based progression system by helping determine the logical order and timing of activities throughout the simulation.

This system allows the game to simulate a realistic project schedule. The player must manage the order of activities carefully because delays or poor decisions in one area can create problems in later stages.

Time and Progression System

The game follows a week-based project timeline. The festival is planned to take place in Week 11. Activities are distributed across the earlier weeks, and each activity has an expected completion period. The original plan requires the player to complete all major planning activities by the end of Week 8.

However, the game also includes Week 9 and Week 10 as buffer periods. If the player cannot complete all required activities by the end of Week 8, they can continue working during these additional weeks. This creates flexibility and simulates real-world project delays. At the same time, using the buffer period creates a schedule penalty because the project moves beyond its original planned scope.

If the player still cannot complete all required activities by the end of Week 10, the project is considered unsuccessful, and the game ends before the festival can be executed. This mechanism emphasizes the importance of time management, planning, and meeting deadlines.

Resource Management System

The game also includes a resource management system. At the beginning of the game, the player has a limited number of team members, phones, and computers. Team members are required to complete activities, phones are used for communication-related tasks, and computers are used for operational and administrative tasks. If the available resources are not sufficient, task completion may become slower, and the project may face delays. The player can purchase additional resources, but this reduces the available budget. Therefore, the implementation creates a trade-off between operational efficiency and financial control.

Budget System

Budget is one of the central variables in the game. The player starts with a fixed initial budget, and almost every activity affects this budget. Some decisions increase the budget, such as accepted sponsorships and ticket revenue. Other decisions reduce it, such as finding artists, buying promotion options, choosing stage and sound systems, purchasing decorations, conducting emergency training, or acquiring additional resources.

The budget is updated dynamically after each relevant decision. This allows the player to immediately see the financial consequences of their choices. The budget system encourages the player to think strategically and balance quality, risk, and cost.

Scenario System and Festival Day

Festival Day takes place at the beginning of Week 11, after the end of Week 10, and represents the execution phase of the project. Unlike the previous stages, Festival Day does not include regular planning activities. Instead, the player faces random scenarios that test the quality of earlier decisions.

In addition, random activity-based scenarios are integrated throughout the gameplay, not only during Festival Day. During different project activities, players may encounter unexpected situations and mini-scenarios related to the current task, requiring them to make quick decisions under changing project conditions. These random scenarios increase the dynamic nature of the simulation and improve the realism of the project management experience.

These scenarios include different types of problems, such as electrical failures, crowd control issues, medical incidents, weather disruption, VIP complaints, delivery problems, and team motivation issues. The outcome of these scenarios depends on previous choices such as emergency training, team assignment, transport coordination, layout planning, and resource allocation.

For example, if the player trained team members in electrical failure response, the team can handle power-related scenarios more efficiently. If the player made poor transport coordination decisions, setup-related risks may become more difficult to manage. This creates a connection between the planning phase and the execution phase.

Scoring and Final Evaluation

At the end of the game, the player receives a final evaluation based on multiple performance dimensions. The scoring system does not rely on a single result. Instead, it evaluates the player’s overall project management performance through several criteria, including participant satisfaction, event quality, overall festival success, scope adherence, time management, and budget control.

Participant satisfaction is influenced by decisions such as entertainment selection, food vendors, sound system, decoration theme, volunteers, and clubs. Event quality is affected by attendance, promotion reach, engagement level, and operational effectiveness. Scope adherence checks whether the player completed the mandatory project requirements, such as forming a team, selecting sponsors, meeting artist requirements, providing food vendors, and ensuring cleaning and security services. Budget control evaluates whether the player managed financial resources effectively.

The final evaluation provides feedback on both successful decisions and areas that need improvement. This feedback helps the player understand the consequences of their choices and reflect on project management principles.

Overall Implementation Logic

Overall, the Godot implementation of PMSG is based on interconnected activity panels, shared game state variables, time-based progression, conditional unlocking, resource limitations, and decision-based scoring. Each activity updates important variables such as budget, selected team, expected attendance, satisfaction, event quality, layout compatibility, and project progress. These variables are then used in later activities and in the final evaluation.

The game follows the project lifecycle of planning, decision-making, execution, risk response, and evaluation. By combining activity dependencies, budget management, resource allocation, scenario-based challenges, and final scoring, the game creates a realistic and educational project management simulation.

In addition, the implementation also integrates CPM (Critical Path Method) logic into the activity dependency structure. Activities are connected through prerequisite relationships, and the project schedule is organized according to these dependencies. This allows the system to simulate realistic project sequencing, identify critical activities that directly affect project completion time, and emphasize the importance of scheduling and dependency management within the overall gameplay.

# RESULTS & DISCUSSION

The main result of this project is the development of a functional project management simulation game prototype based on a university festival scenario. The project successfully transformed the original educational idea into an interactive software application where the player takes the role of a project manager and makes decisions under time, budget, scope, and resource constraints. The current version includes the opening screen, university message, project timer, activity-based flow, and decision screens for the main project activities.

The initial objectives of the project were realized to a significant extent. The game allows the player to experience planning, resource allocation, budgeting, cost management, risk preparation, and performance evaluation through different festival management activities. Activities such as team assignment, work assignment, sponsor management, promotion strategy, ticket pricing, volunteer/club recruitment, food vendor selection, stage and sound system choices, transport coordination, decoration theme decision, cleaning and security planning, and layout-related decisions are implemented as playable modules. In these activities, the player can compare alternatives, make selections, and observe how decisions affect project-related outcomes.

One of the main achievements of the project is that it connects project management concepts in a single decision-based environment. Instead of teaching time, budget, scope, resources, and risk management separately, the game shows how these dimensions affect each other. For example, selecting better artists or equipment may improve event quality, but it also increases cost. Choosing more training may improve emergency preparedness, but it reduces the available budget and time. Similarly, sponsor decisions can improve the budget, but they include uncertainty due to acceptance probabilities. Therefore, the game supports the original objective of helping players understand project trade-offs in a realistic way.

The project also achieved its objective of creating a structured project lifecycle experience. The player begins with a project briefing and progresses through the activities according to the festival preparation process. This supports learning objectives related to project planning, task prioritization, timeline awareness, and resource allocation. The current implementation also includes visual and numerical feedback mechanisms such as charts, decision indicators, budget changes, and performance-related outputs. These elements help the player monitor project progress and understand the consequences of their decisions.

However, some objectives were only partially realized and will be completed in the final development stage. The Festival Day scenarios have not yet been fully implemented. Therefore, the risk response objective is currently represented mainly through preparation-based activities such as emergency training and sponsor rejection risks. In the final version, Festival Day will include unexpected situations such as electrical failure, crowd control problems, medical incidents, and crisis management scenarios. These scenarios will allow the player to test whether earlier risk preparation decisions were effective. In addition, the game currently supports schedule awareness through the project flow and Gantt chart logic, but the feature that allows the player to create their own Gantt chart will be added as a further improvement.

Compared with the initial objectives, the main purpose of the project did not change. The project was originally planned as an educational simulation game that teaches project management through active decision-making, and this purpose remained consistent throughout the development process. The main differences occurred in implementation details. Due to time and feasibility limitations, the team prioritized the core activity modules, decision mechanisms, and playable structure before adding more advanced features. As a result, Festival Day scenarios and user-created Gantt chart generation were postponed to the final development stage.

Overall, the project can be considered successfully completed as a functional current version of the game. The core game structure, major activity screens, timer, decision flow, and project management mechanics are implemented. Although some advanced features are still under development, the current version of the game already demonstrates the main purpose of the project. It allows players to experience important project management concepts such as planning, budgeting, resource allocation, risk preparation, scope control, and performance-based decision-making.

The project also provides a meaningful contribution compared with traditional project management learning methods. Conventional project management education often relies on lectures, formulas, written case studies, or isolated planning exercises. This project combines several project management dimensions in one interactive and student-centered environment. Its contribution is not the invention of a new project management theory, but the integration of project planning, budgeting, resource management, risk preparation, scoring, and festival operations into a single educational game. Since the university festival scenario is familiar and relatable for students, the game also increases engagement and supports experiential learning.

From an environmental perspective, the proposed solution has a low carbon footprint because it is a software-based educational tool and does not require physical production, printed materials, transportation, or disposable resources. For the carbon footprint estimation, the functional unit is defined as one 1-hour gameplay session on a standard laptop. A standard laptop is assumed to consume approximately 50–100 Wh during one hour of use. This corresponds to 0.05–0.10 kWh of electricity consumption. EnerGuide states that a laptop typically uses about 50–100 Wh while in use, depending on the model.

Using Türkiye’s grid emission factor of approximately 0.5 kg CO₂e/kWh, the estimated operational carbon footprint can be calculated as follows. The World Bank states that Türkiye’s grid emission factor is around 0.5 kg CO₂e per kWh.

Carbon footprint = Electricity consumption × Grid emission factor

Minimum estimate:

0.05 kWh × 0.5 kg CO₂e/kWh = 0.025 kg CO₂e

Maximum estimate:

0.10 kWh × 0.5 kg CO₂e/kWh = 0.05 kg CO₂e

Therefore, the estimated carbon footprint of the proposed solution is approximately 0.025–0.05 kg CO₂e per 1-hour gameplay session. This estimate includes only operational electricity use during gameplay and excludes embodied emissions from laptop manufacturing. Compared with conventional alternatives such as printed training materials, physical workshops, or in-person simulation sessions, the proposed digital solution is expected to have a lower environmental impact because it does not require paper use, physical transportation, printed resources, or repeated material production.

In terms of economic feasibility, the proposed solution is practical and cost-efficient. The game is developed as a lightweight 2D simulation using the Godot Engine, which reduces the need for expensive software licenses or high-performance hardware. Since the solution is digital, it does not require physical production, inventory, distribution, or a complex supply chain. Once developed, the game can be reused by many students with minimal additional cost. This improves supply chain efficiency because the educational material can be distributed digitally rather than through printed or physical resources.

The project also supports circularity and resource efficiency. Since the game is reusable, it can replace repeated physical training materials and can be updated through software improvements instead of being reproduced from scratch. New activities, scenarios, or scoring mechanisms can be added in future versions without creating material waste. Therefore, the proposed solution is economically feasible and environmentally efficient as a reusable digital learning tool.

In conclusion, the results show that the project achieved its main educational and technical goals. The current version of the game successfully demonstrates how project management concepts can be taught through interactive decision-making. Although Festival Day scenarios and the user-created Gantt chart feature still need to be finalized, the core system is functional and aligned with the initial project objectives. The project offers an engaging, reusable, low-cost, and low-carbon educational solution for learning project management.

# IMPACT

The Project Management Simulation Game (PMSG) provides educational, technological, and socio-economic impact by offering an interactive environment in which users experience the complete lifecycle of a project under realistic constraints. Unlike traditional theoretical approaches to project management education, the proposed system allows players to actively engage in planning, scheduling, budgeting, resource allocation, risk management, and decision-making processes within a dynamic simulation environment. Through this approach, the project contributes to improving practical understanding of project management concepts and strengthens decision-making skills under time, budget, and scope limitations.

One of the major educational contributions of the project is its ability to simulate realistic project dependencies and operational challenges. Throughout the game, players are required to manage interconnected activities, allocate limited resources, respond to unexpected scenarios, and balance competing priorities. This structure allows users to observe the consequences of their decisions directly and understand the importance of strategic planning and coordination. The simulation also supports experiential learning by enabling users to apply theoretical project management knowledge in a practical and interactive setting. As a result, the project can contribute to improving analytical thinking, leadership, teamwork, and crisis management skills.

From a technological perspective, the project demonstrates the implementation of a complex decision-based simulation system using the Godot Engine. The system integrates activity dependency structures, dynamic scoring mechanisms, resource management models, timeline-based progression systems, and scenario-driven gameplay mechanics within a unified architecture. The implementation of interconnected decision systems allows changes in one area of the project to influence later stages of the simulation, creating a more realistic representation of project management processes. Additionally, the inclusion of emergency response scenarios, schedule flexibility mechanisms, and performance evaluation systems increases the realism and educational value of the simulation environment.

The project also includes innovative aspects in terms of educational gamification and simulation-based learning. Instead of relying solely on static project management case studies or theoretical lectures, the proposed solution transforms project management education into an interactive and adaptive experience. This approach has the potential to increase user engagement and improve learning effectiveness. Furthermore, the system can be expanded and adapted for use in academic environments, workshops, or professional training programs. With further development, the project may also support additional features such as multiplayer collaboration, AI-supported decision systems, advanced analytics, or online educational integration, increasing its long-term applicability and scalability.

Regarding commercial and entrepreneurial potential, the simulation framework may be adapted into a broader educational training platform for universities, project management courses, and organizational training programs. Since the system models realistic management constraints and operational challenges, it may provide value as a supplementary educational tool for project management and operations management training. The modular structure of the project also allows future customization for different industries or event management scenarios.

In terms of Freedom-to-Use (FTU) considerations, no major FTU limitations were identified during the development process. The project was implemented using the open-source Godot Engine, and the materials used within the project were either originally produced by the team or obtained from royalty-free and open-source resources. External assets, icons, and visual elements were selected carefully to avoid copyright violations. Therefore, the project does not currently present significant legal or licensing conflicts related to software or content usage.

The project also provides several environmental and sustainability-related benefits due to its digital and simulation-based nature. Traditional project management training methods may require physical workshops, printed materials, or real-life operational exercises, all of which consume additional physical resources and generate waste. In contrast, the proposed solution provides a reusable digital learning environment that minimizes physical resource consumption. The simulation can be used repeatedly without additional material costs, reducing paper usage and unnecessary operational overhead. Furthermore, the system encourages efficient resource utilization by requiring players to optimize limited budgets, manage operational constraints, and minimize inefficient planning decisions throughout the gameplay process.

From a sustainability and circularity perspective, the project promotes efficient planning and resource optimization principles. The simulation emphasizes the importance of balancing operational efficiency, financial limitations, and resource allocation, which reflects sustainable engineering and management practices. Since the software architecture is reusable and expandable, the system can continue to be improved and adapted for future educational purposes without requiring the redevelopment of the entire platform. This modular and reusable structure contributes to sustainable software development practices by supporting long-term maintainability and adaptability.

Overall, the Project Management Simulation Game contributes to project management training through an interactive, technology-supported, and sustainability-aware simulation environment. By combining educational objectives with realistic operational constraints and dynamic decision-making systems, the project provides both practical learning opportunities and a scalable foundation for future development and educational applications.

# ETHICAL ISSUES

As stated in the initial draft proposal, the only ethical consideration identified for the Project Management Simulation Game (PMSG) concerns potential copyright issues. Since the submission of the Initial Design Proposal, no additional ethical issues have arisen during the development process. All materials used in the project, including images, icons, and design elements, are either originally created by the team or obtained from royalty-free and open-source platforms. Proper attribution is provided whenever external resources are used. Furthermore, the simulation scenarios do not involve ethical dilemmas or decision-making situations that would require players to make ethical judgments.

# PROJECT MANAGEMENT

## Initial Project Plan

At the beginning of the project, our initial plan was to develop a project management simulation game that focused mainly on basic project planning concepts such as task assignment, scheduling, budgeting, and resource management. The game was planned as a relatively simple festival management simulation developed in the Godot Engine with a linear gameplay structure. We initially aimed to include core activities such as team selection, sponsor management, ticket pricing, and festival layout planning. The first project plan also included the use of CPM and PERT methods to integrate project management theory into the gameplay.

## Changes During Implementation

During the implementation process, the project evolved significantly compared to the initial plan. As development progressed, we expanded the game by adding more detailed mechanics, including emergency training systems, dynamic risk scenarios, scoring systems, workload balancing, and festival-day events. The project also became more modular, with activities implemented as separate panels connected through a centralized game state structure in Godot.

Some planned features were simplified or redesigned due to technical and time limitations. For example, certain dynamic systems were converted into predefined scenario-based events to ensure stability and completion within the project timeline. In addition, the layout planning system became more interactive than originally planned, and more emphasis was placed on balancing educational value with gameplay experience. During our meetings with our supervisor, we also discussed the idea of allowing players to purchase additional information using in-game money. Based on these discussions, we added mechanics such as consulting systems and information-revealing options, where players can spend part of their budget to obtain more accurate estimates or hidden project information before making decisions. This addition strengthened the relationship between budget management and decision-making under uncertainty.

Throughout the implementation, we continuously revised activity structures, user interface designs, and scoring calculations in response to testing and integration challenges.

## Final Project Plan /Lessons learned

In the final version, the project became a much more comprehensive educational simulation than we initially planned. The final game includes interconnected decision-making systems covering time, budget, scope, resource management, risk management, and participant satisfaction. The modular architecture also made the project easier to expand and maintain.

One of the most important lessons we learned was the importance of flexibility in project management. Even with an initial project plan, many changes became necessary during development due to technical constraints, integration problems, and gameplay balancing needs.

We also learned that communication and task distribution within the team were critical for managing a large software project effectively.

Another important lesson was that simplifying certain systems can sometimes improve both usability and project completion efficiency.

Overall, the project helped us better understand how theoretical project management concepts are applied in real software development processes.

# CONCLUSION AND FUTURE WORK

## Conclusion

This project developed a functional educational simulation game that teaches project management concepts through a university festival scenario. The player acts as a project manager and makes decisions under constraints on time, budget, scope, and resources. The game includes major project activities such as team assignment, sponsor management, promotion strategy, ticket pricing, entertainment line-up, vendor selection, resource management, layout planning, and final evaluation. Through these activities, the current version of the game shows how different project decisions affect Budget Control, Time Management, Scope Adherence, Participant Satisfaction, and Event Quality.

The project successfully connects project management methods with interactive gameplay. CPM was used to analyze the activity network, identify critical activities, and calculate total slack values. The decision and scoring mechanisms were also designed to show realistic trade-offs. For example, high-quality decisions may improve satisfaction and event quality but increase costs, while cheaper options may protect the budget but reduce performance.

Although the current version of the game achieves the main educational objective, some features still need further development. Future work should focus on completing Festival Day scenarios , improving the resource leveling system, allowing more interactive Gantt chart decisions, and expanding the final KPI-based evaluation screen. User testing with students should also be conducted to evaluate usability, difficulty level, and educational effectiveness. Based on this feedback, the interface, activity manuals, scoring thresholds, and decision tables can be improved.

## Future Work

In future versions, the game can also be made more sustainable and cost-efficient by keeping it lightweight, reusable, and easy to distribute digitally. Since it is developed in Godot, it can be shared without expensive software licenses and used repeatedly in project management or industrial engineering courses. Although the current version is designed around a university festival scenario, the same simulation logic can potentially be adapted to different project contexts in the future, such as conference planning, product launch management, or emergency response planning. However, this is not presented as a direct promise of the current project, but rather as a possible long-term development direction.

Another possible improvement is to make the simulation more player-driven. In the current version, many activity rules, decision tables, and evaluation criteria are predefined by the system. In future versions, more flexible mechanisms can be developed so that project outcomes depend more on the player’s own planning choices, selected strategies, and customized project settings. This would reduce the number of fixed assumptions defined by the developers and allow the game to evaluate project performance in a more adaptive way. Overall, the project provides a strong foundation for an interactive, low-cost, and reusable project management learning tool.

# APPENDIX

Appendix A. Decision Table Values and Balancing Logic

This appendix presents the main decision table components used in the game. Each activity includes different decision variables such as cost, quality, capacity, efficiency, popularity, safety, space requirement, or satisfaction impact. These values were designed to create a balanced gameplay structure. The purpose was to make random choices uncertain, while allowing players to obtain better outcomes through strategic comparison of alternatives.

| Activity | Main Decision Table Components |
| --- | --- |
| Team Assignment | Team member attributes, 8-person team selection logic, average performance threshold |
| Sponsor Management | Sponsor score variables, contribution values, average sponsor score threshold |
| Promotion Strategy | Expected reach, reliability, cost logic |
| Entertainment Line-Up | Artist type, popularity, cost balancing, 1 headliner + 2 supporting artist rule |
| Volunteer/Club Recruitment | Engagement level, activity type, number of selections, space requirement |
| Food Vendor Selection | Service capacity, speed, hygiene, cuisine type, electricity, space, efficiency score |
| Stage Setup Choice | Stage size, performance score, stage area demand |
| Sound System Choice | Sound system score, installation/technical requirements |
| Decoration Theme Decision | Theme score, satisfaction impact, space/time effects |
| Cleaning and Security | Cleaning/security type, performance and cost logic |

These decision table values support the main gameplay logic by forcing the player to consider trade-offs. For example, an option with higher quality or efficiency may also have a higher cost, while a cheaper option may reduce participant satisfaction or event quality.

Appendix B. Price Determination Formulas

This appendix explains how the prices of alternatives were determined. Prices were not assigned completely randomly. Instead, they were generally connected to the performance, efficiency, quality, or expected impact of each option. A normalization method was used to place each alternative within a reasonable price range. A random variation term was also added to make the values more realistic and to prevent a perfectly linear pricing pattern.[GU1]

Normalized Score =Current Score - Minimum ScoreMaximum Score - Minimum Score x 100

In this structure, alternatives with higher normalized scores are generally placed closer to the maximum price, while alternatives with lower normalized scores are placed closer to the minimum price. The random variation term introduces small differences among alternatives, making the dataset more natural.

| Activity | Min Price | Max Price | Random Variation |
| --- | --- | --- | --- |
| Sponsor Management | 100,000 | 400,000 | ±20,000 |
| Promotion Strategy | 20,000 | 50,000 | ±10,000 |
| Food Vendor Selection | 40,000 | 100,000 | ±10,000 |
| Stage Setup Choice | 100,000 | 250,000 | ±40,000 |
| Sound System Choice | 80,000 | 150,000 | ±10,000 |
| Decoration Theme Decision | 80,000 | 150,000 | ±10,000 |
| Cleaning and Security | 40,000 | 80,000 | ±10,000 |

This pricing logic helps create realistic budget trade-offs. Higher-performing options usually require more spending, but the random variation prevents players from identifying an overly simple pattern.

Appendix C. Scoring Criteria

This appendix summarizes the main scoring criteria used in the final evaluation of the game. The game does not calculate a single overall score. Instead, the player is evaluated separately based on five key performance indicators: Scope Adherence, Participant Satisfaction, Event Quality, Budget Control, and Time Management.

| Score Category | Detailed Criteria | Scoring Logic |
| --- | --- | --- |
| Scope Adherence | Team performance, sponsor number, sponsor score, attendance target, artist type, volunteer/club activity types, food variety, hygiene, cleaning/security | Based on 12 scope requirements. Each met requirement has equal weight. Score = number of met requirements divided by 12 and converted to 100. |
| Participant Satisfaction | Entertainment popularity, volunteer engagement, sound system score, decoration theme score | Based on 4 satisfaction requirements. Each met requirement has equal weight. Score = number of met requirements divided by 4 and converted to 100. |
| Event Quality | Ticket attendance, promotion reach, entertainment crowd appeal, activity diversity | Based on total estimated attendance. The score is calculated by comparing attendance within the range of 0 to the target attendance level. As attendance gets closer to the target, the score increases proportionally. If the attendance exceeds the target, the score is kept at 100 and does not increase further. |
| Budget Control | Initial budget, income sources, cost items, -300,000 failure threshold, scholarship fund | Based on the final remaining budget. A final budget of 400,000 TL or more gives 100 points. A budget between 0 and 400,000 TL is scaled proportionally. If the budget falls below -300,000 TL, the score becomes 0 and the project fails. |
| Time Management | Activity completion before the festival day, expected activity durations, delay level, critical/non-critical activity status, fixed festival deadline | Based on weighted activity completion. Critical activities have higher weight because they directly affect the project schedule, while non-critical activities have lower weight. If an activity is completed on time or before its expected duration, it receives full points. If it is completed late, it receives partial points depending on the delay level. If it is not completed before the festival day, it receives 0 points. The total score is normalized to 100. |

Appendix D. Scope Adherence

Scope Adherence measures whether the player met the basic requirements to organize a festival. This score checks whether the player satisfied the minimum project scope conditions across the team, sponsors, attendance, entertainment, volunteer/club activities, vendors, and cleaning/security.

| Activity | Scope Requirement | Status |
| --- | --- | --- |
| Team Assignment | Overall average team performance should be higher than 2.5 | [Met / Not Met] |
| Sponsor Management | At least 2 sponsors should be selected | [Met / Not Met] |
| Sponsor Management | The average sponsor score should be higher than 2.5 | [Met / Not Met] |
| Sponsor Management | Sponsor budget contribution should satisfy the required level | [Met / Not Met] |
| Ticket Pricing Strategy | Attendance should be at least 3000 participants | [Met / Not Met] |
| Entertainment Line-up | The average popularity level should be higher than 3 | [Met / Not Met] |
| Entertainment Line-up | At least 1 main headliner and 2 supporting artists should be selected | [Met / Not Met] |
| Volunteer/Club Recruitment | Required activity types should be covered: competitive, artistic, informational, and interactive | [Met / Not Met] |
| Volunteer / Club Recruitment | At least 2 volunteers and 3 clubs should be selected | [Met / Not Met] |
| Food Vendor Selection | Required cuisine types should be covered | [Met / Not Met] |
| Food Vendor Selection | The average hygiene rating should be higher than 2.5 | [Met / Not Met] |
| Festival Cleaning & Security | At least 1 cleaning crew and 1 security team should be selected | [Met / Not Met] |

Appendix E. Participant Satisfaction

Participant Satisfaction measures how satisfied participants are with the overall festival experience. This score is based on four main participant-facing elements: entertainment quality, volunteer/club engagement, sound system performance, and decoration theme attractiveness.

| Activity | Requirement | Status |
| --- | --- | --- |
| Entertainment Line-up | The average popularity level should be higher than 4 | [Met / Not Met] |
| Volunteer / Club Recruitment | The average engagement level should be higher than 6 | [Met / Not Met] |
| Sound System Choice | The sound system score should be higher than 5 | [Met / Not Met] |
| Decoration Theme Decision | The theme score should be at least 0.5 | [Met / Not Met] |

Appendix F. Time Management Score Logic

The Time Management score is calculated by summing the points earned from all project activities. Each activity has a point value based on its importance in the project schedule. Critical activities are worth 8 points, while non-critical activities are worth 4 points. The total maximum score is 100 points.

For each activity:

Activity Time Scorei​=Activity Pointi × Delay Multiplieri

Final score:

Time Management Score=i=115Activity Time Scorei

The delay multiplier is determined by comparing the actual duration with the expected duration of the activity. If the activity is completed on time or earlier, the player receives the full point value. If the activity is delayed, the point value is reduced according to the delay level. If the activity is not completed before the festival day, the activity receives zero points.

| Activity Status | Delay Condition | Score Multiplier | Critical Activity Contribution | Non-critical Activity Contribution |
| --- | --- | --- | --- | --- |
| Completed on time or earlier | Finished within the expected duration | 100% | 8 points | 4 points |
| Completed with a small delay | Delay is up to 25% of the expected duration | 80% | 6.4 points | 3.2 points |
| Completed with moderate delay | Delay is between 25% and 50% of the expected duration | 60% | 4.8 points | 2.4 points |
| Completed with a major delay | Delay is between 50% and 100% of the expected duration | 40% | 3.2 points | 1.6 points |
| Completed very late | Delay is more than 100% of the expected duration, but the activity is completed before the festival day | 20% | 1.6 points | 0.8 points |
| Not completed before festival day | Activity is unfinished when the festival starts | 0% | 0 points | 0 points |

Appendix F. The Github

https://github.com/oozankoyuncu/Bitirme-Projesi

This appendix provides the GitHub repository link for accessing the game source code.

# REFERENCES

Energuide. (n.d.). How much power does a computer use? And how much CO₂ does that represent? Retrieved May 10, 2026, from https://www.energuide.be/en/questions-answers/how-much-power-does-a-computer-use-and-how-much-co2-does-that-represent/54/

World Bank. (2022). Power sector decarbonization pathways in Türkiye. World Bank Group. Retrieved May 10, 2026, from https://documents1.worldbank.org/curated/en/099005306072229994/pdf/P177479071a62900d08653003d77ed215d3.pdf

.